Acquisition Management System Guidance

Initial Investment Analysis Plan Guidance and Template

September 2024

Office of Investment Planning and Analysis

AFI-1

Federal Aviation Administration

800 Independence Avenue SW

Washington, DC 20591

Purpose

This document guides development of the initial Investment Analysis Plan (IAP). The plan outlines the activities required per AMS policy and the JRC Secretariat Readiness Checklist for an investment initiative to achieve an Initial Investment Decision. As applicable, the work builds on that done in previous stages of the AMS lifecycle. The included template provides the format and content for the plan.

Relationship to AMS

The plan for initial investment analysis is required for all New Initiative acquisition categories. It is developed late in Concept and Requirements Definition (CRD), after the alternatives are determined and is approved at the Investment Analysis Readiness Decision (IARD).

For all other investment initiatives (which are exempt from initial investment analysis), a plan for final investment analysis is developed late in Concept and Requirements Definition and approved at the Investment Analysis Readiness Decision.  The Final Investment Analysis plan and guidance are discussed in a separate document.

Who prepares it

The service organization develops the initial Investment Analysis Plan with assistance from AFI-1.

Initial Investment Analysis Plan

FOR

Name of Initiative

Approved by:

_______________________________	                 Date:_________________ Requesting Organization1

Approved by:

_______________________________	                 Date:_________________ Performing Organization 2

Approved by:

_______________________________	                 Date:_________________
Director, Investment Planning & Analysis (AFI-1)

1 Organization requesting the IARD decision. Signature level determined by Investment Analysis Team (IAT).

2 Organization performing the IID analysis outlined in the plan. If the requesting organization is the same as the performing organization, delete this signature line. Signature level determined by IAT.

Contact Point

Name

Title

Phone Number

Email Address

Federal Aviation Administration
800 Independence Avenue
Washington, D.C. 20591

TABLE OF CONTENTS

1.0	Introduction	1

1.1	Purpose	1

1.2	Decision Requested	1

1.3	Acquisition Strategy	1

2.0	PROGRAM Overview	1

2.1	Scope	2

2.2	Legacy Case Description	2

2.3	Description of Alternatives	2

3.0	Major Constraints, ASSUMPTIONS, and Ground rules	2

3.1	Constraints	2

3.2	Assumptions	2

3.3	Ground Rules	3

4.0	INVESTMENT Analysis Approach	3

4.1	Strategy	3

4.2	Analysis Activities and Products	4

4.2.1	Lifecycle Cost Analysis	4

4.2.2	Benefits Analysis	4

4.2.3	Risk Analysis	6

4.2.4	Human Factors Assessment	6

4.2.5	Schedule Analysis	7

4.2.6	Economic Analysis	7

4.2.7	Budget Assessment	7

5.0	IP&A Independent Evaluation Review	8

6.0	EXIT CRITERIA	8

7.0	Decision Briefing	8

8.0	ROLES AND RESPONSIBILITIES	8

8.1	Program Office	8

8.2	Relationship with IP&A	9

APPENDICIES

APPENDIX A:  INVESTMENT ANALYSIS TEAM COMPOSITION ……………………………………..…A-1

APPENDIX B:  INVESTMENT ANALYSIS SCHEDULE ……………………………………………….……B-1

# Introduction

The plan outlined in this document directly follows from the required activities per AMS policy and the JRC Secretariat Readiness Checklist . The JRC Executive Secretariat Support Staff conduct weekly Readiness meetings at 10 AM each Thursday to discuss the status of investment initiatives seeking decisions and the scheduling of decision meetings. When an initiative is about 3-4 months from its investment decision date, it needs to come prepared to discuss the status of the initiative it wishes to add to a JRC meeting agenda.  Prior to appearing before the JRC to request a decision, the program office must complete the readiness criteria applicable to the decision being requested. This must be done two weeks prior to your JRC meeting date.

## Purpose

Example:

This plan describes the strategy, analysis activities, and products that will be completed to obtain an Initial Investment Decision from the Joint Resources Council for (Name of Initiative). An Initial Investment Decision is planned for mm/yyyy.

## Decision Requested

Example:

The program office will request the Joint Resources Council to approve the Initial Investment Decision to include the following:

Down selection to one alternative

Planning funds for final investment analysis (if required)

Approval to release a Screening Information Request to vendors for the solution and continue towards Final Investment Decision (FID).

Approval of the plan for final investment analysis.

## Initial Acquisition Strategy

This section should present a high-level overview about what is currently known of the acquisition approach, including whether a competitive procurement will be done or if an existing contract will be used

# PROGRAM Overview

This section should reflect conclusions previously substantiated and documented in the Shortfall Analysis Report and Range of Alternatives. Briefly summarize the content of those documents in this section and provide contact points so that initial investment analysis stakeholders can easily access electronic versions to gain a deeper understanding of the issues at hand.

## Scope

Identify the specific problem or opportunity this investment initiative will address. Describe the impact if not addressed.  If segmentation has been considered during development of the Range of Alternatives, document the rationale for the conclusions that were reached.  If segmentation is not being utilized, a description for why segmentation would not be applicable should be given.

The FAA defines a useful segment as:

A useful segment is an economically and programmatically separate segment that provides direct value to the agency, that would still apply even if separated from the overall program, or is used to reduce programmatic, acquisition, and/or technical risk around development and implementation of the asset(s) procured. A useful segment must be fully funded with regular appropriations or other funding streams.

A planning segment of a capital project is a type of useful segment that provides information which allows the agency to develop the design; assess the benefits, costs, and risks; and establish realistic baseline cost, schedule, and performance goals before proceeding to full acquisition of the useful asset (or canceling the acquisition). Typically, planning segments should be separate from asset procurement.  This approach allows for modular contracts and more effective risk allocation between the agency and vendors.

## Legacy Case Description

The Legacy Case provides an understanding of how the National Airspace System (NAS) operates today so that decision makers can understand what changes the proposed investment will buy.  There must be a clear relationship between the Legacy Case and the specific problem or opportunity this investment initiative will address.

## Description of Alternatives

Using the Range of Alternatives document signed by ANG-B or ASP-1, briefly summarize each alternative technically and operationally that will be evaluated during initial investment analysis. Briefly describe potential advantages and disadvantages of each alternative.

# Major Constraints, ASSUMPTIONS, and Ground rules

## Constraints

Constraints can be on both analytical resources as well as scope/schedule/cost. Analytical resource constraints could mean staffing issues on cost/schedule/benefit analyses. It could also mean constraints on data sources required to develop the business case. Programmatic scope constraints could be determined by analysis of the Enterprise Architecture, FAA Strategic Initiatives, and NextGen Implementation Plan.   Programmatic schedule constraints could be based on Agency commitments to key stakeholders or instances where contracts dictate the timing of Agency decisions. Programmatic cost constraints can relate to affordability analyses as well as external cost drivers.

## Assumptions

Briefly outline assumptions made for the purposes of reaching the IID.  Constrain the list of assumptions to uncertain future conditions (removed from further analysis) that can be used as inputs in other aspects of initial investment analysis.

Example:

A preliminary list of assumptions was developed during concept and requirements definition.  This list will be revised as analysis and research provide more detailed information. The updated list will form the basis for the cost, schedule, benefit, and risk analysis of each alternative, as well as their associated Basis of Estimate documents.  Current high-level assumptions include:

- (list major assumptions)

## Ground Rules

Ground rules are a common set of agreed upon estimating standards that provide guidance and minimize conflicts in definitions. Ground rules are used to specify a manner of analysis with a view toward reducing the amount of analysis where it makes sense to do so.  The value of a ground rule is that it eliminates some procedural choices that might otherwise be addressed through time-consuming sensitivity analyses. A ground rule might specify that a cost effectiveness assessment be accomplished rather than a cost-benefit analysis, or might specify the analytical period to be used for the study. Ground rules are useful when they answer policy or procedural questions that might otherwise consume time and resources unnecessarily.

Example:

The investment analysis team will develop an appropriate set of ground rules to standardize and streamline the analysis of alternatives.

# INVESTMENT Analysis Approach

## Strategy

Briefly describe the methods and tactics the investment analysis team will follow in conducting the initial investment analysis. If a program is multi-segmented and does not have a justifiable business case until after multiple segments are complete, it likely will be necessary to include cost, schedule, and benefit information estimates for future segments as well for the purposes of the economic analysis. It is important to note that it may be the case that the value a segment provides could be in enabling follow on segments, even if the segment itself does not realize the full benefits of the investment.

Example:

This analysis will evaluate each (investment initiative) alternative, determine their economic value, and evaluate their ability to resolve the shortfall. The investment analysis team will design the analysis to clearly identify and quantify the incremental schedule, risks, benefits, and costs of major components of each alternative, and will clearly establish the business value of the investment when compared against the quantified shortfall. Benefits will include both quantitative measures and qualitative considerations.

The analysis will (1) assist in identifying and defining opportunities for segmentation for the alternatives; and (2) identify, evaluate, and document the impact that constraints have on the initiative.

## Analysis Activities and Products

This section of the plan addresses each activity and product required during initial investment analysis. These are a subset of the decision- point products specified in the FAA JRC Secretariat Readiness Checklist as of August 17, 2016.

Example:

This program initiative has been designated as a New Initiative ACAT (1-5 as appropriate) (type & category) and is required to perform the following analytical activities and produce the following products:

- Enterprise Architecture products and amendments

- Comparative risk assessment including safety

- Initial information systems security assessment

- Spectrum requirements

- Assessment of enterprise infrastructure services

- Integrated logistics support assessment

- Preliminary Test and Evaluation Master plan

- Initial Program Requirements Document

- Initial Implementation Strategy and Planning Document for each alternative

- NextGen impact and alignment assessment

- Initial business case for each alternative

- Final investment analysis plan

- Independent evaluation review by IP&A

In subsequent sections, the IID stakeholders can expand on the plan to accomplish the checklist items. Not all checklist items must be expanded on only those where stakeholder engagement shows significant value in a more thorough planning of the work to be performed.

### Lifecycle Cost Analysis

The investment analysis team will develop cost models consistent with Office of Investment Planning and Analysis (IP&A) guidance in the “Guide to Conducting Business Case Cost Evaluations” . Specific cost estimating requirements by ACAT and decision point are defined in the “Business Case Analysis Guidance, Appendix A”. If the investment analysis team has worked with IP&A to tailor or modify their cost-estimating approach, that agreement should be documented here.

Example:

The investment analysis team will develop a lifecycle cost estimate for each alternative and the legacy case. The team will use the latest FAA Standard Work Breakdown Structure to identify cost elements. A supporting cost Basis of Estimate will accompany the cost estimates. The team will develop the estimate according to the “Guide to Conducting Business Case Cost Evaluations”. The lifecycle will start at the beginning of the Service Analysis & Strategic Planning (SASP) phase and extend for a period of 20 years from the last system commissioning, e.g., FY20 to FY45. Additionally, the lifecycle cost estimate will be risk-adjusted.

### Benefits Analysis

Benefits estimates will be developed using accepted operations research models. Verifiable descriptions of benefit estimate methodologies and data sources will be included in the benefit Basis of Estimate. See the benefits analysis section of the IP&A website at www.ipa.faa.gov.

Example:

The investment analysis team will develop and submit lifecycle benefit estimates with supporting documentation. The measures and rough estimate of the performance shortfall developed during shortfall analysis form the basis for the detailed benefits analysis. The quantified benefits stream will reflect monetized values from a combination of variables. Additionally, the lifecycle benefits will be risk-adjusted.

Any potential overlap between the functions of this investment initiative and those of any other NAS asset (current or future) will be identified, quantified, and documented. Additionally, any identifiable enabling benefits for future programs will be estimated with an agreed to approach for assigning the probability of occurrence.

The approach to estimating and presenting benefits that are difficult to quantify will be agreed to by the Operations Research group and the investment analysis team at the onset of the analysis. In addition to the methodology itself, the data source(s) used to generate those benefits also will be agreed upon by team and the Operations Research group.

Similar to the requirements for the cost estimates, benefits will be risk-adjusted and documented in a Benefits Analysis Report.

### Risk Analysis

The investment analysis team must identify and evaluate medium and high risks associated with each alternative and complete a comparative risk assessment of the alternatives in accordance with FAA risk management policy and guidance (see the risk management page on FAST at http://fast.faa.gov/EMP_Risk_Management.cfm). The investment analysis team must also follow the applicable sections of the PMO’s RIO Management Plan which is consistent with AMS policy.

The team must also identify and evaluate those expectations that could be reasonably treated as assumptions during concept and requirements definition but should be treated as risk issues during investment analysis, including those risk issues from the legacy case definition and shortfall analysis that require further analysis.

Team analysts should consult with appropriate specialty engineering stakeholders and the Specialty Engineering Group Manager to ensure the following engineering topics are integrated in the overall risk assessment of the alternatives (See Section 4 of AMS policy on FAST):

- Reliability, maintainability, availability

- Radio frequency management

- Human factors assessment / operability

- Environmental impact

- Information & system security risk assessment (See Section 4.11 of AMS policy on FAST):

- Supportability and integrated logistics support

- NAS quality assurance and performance

- Enterprise configuration management and operations

- Environment and occupational safety and health

Example:

The investment analysis team will lead the risk assessment effort based on FAA Risk Management practices found on the FAA Acquisition System Toolset (FAST), Acquisition Practices and any applicable risk elements from OMB guidelines outlined in OMB Circular A-11, Part 7 - Planning, Budgeting, Acquisition, and Management of Capital Assets. The risk team will review and validate high and medium risk areas, likelihood of occurrence, and impacts associated with each alternative. Results will be documented and reflected in the schedule, cost, and benefit estimates for each alternative. Statistical risk analysis will be conducted using Monte Carlo techniques to arrive at high-confidence, risk-adjusted lifecycle cost estimates for each alternative.

### Human Factors Assessment

The investment analysis team must assess, and document human factors issues and risks associated with each alternative, and factor them into all business case analyses.

Example:

The investment analysis team will perform a comparative human factors assessment of the alternatives to ensure human-system performance, cost, schedule, and risk are reflected in the business case analysis.

The team will use human factors expertise from the NAS Concept Operations and Service Engineering Group, as well as an internal human factors team, to ensure human factors issues are reflected in all business case cost, benefit, and risk analyses, the IP&A review and report, and the Joint Resources Council briefing.

### Schedule Analysis

In conjunction with analyzing cost and benefits, the investment analysis team must develop program schedules and associated subordinate schedules for FAA investment programs. A separate schedule should be developed for each business case alternative and include all major acquisition and programmatic milestones and supporting activities. It should be aligned with the cost and benefit estimates. The FAA has enterprise licenses for Microsoft Project and Primavera P6 which are the preferred scheduling tools. All schedules are assessed and analyzed using the best practices outlined in the Guide to Conducting Business Case Schedule Evaluations.

Example:

A separate schedule will be developed for each business case alternative that will include all major acquisition and programmatic milestones, supporting activities, and be aligned with cost and benefit estimates. The schedules will define, among other things, when work activities will occur, how long they will take, and how they are related to one another. They will be developed in accordance with the Guide to Conducting Business Case Schedule Evaluations.

### Economic Analysis

Economic analysis compares the time-phased, risk-adjusted costs and benefits of alternatives. The investment analysis team documents the strategy for developing an economic analysis for each alternative.

Example:

The investment analysis team will generate a risk-adjusted benefit/cost ratio and net present value or cost effectiveness assessment, as appropriate, for each alternative. IP&A will perform an economic analysis based on information provided by the team and conduct sensitivity analyses as required.

### Budget Assessment

Example:

IP&A will conduct a budget assessment of the lifecycle cost estimates for each alternative. The program office will assist IP&A in identifying and providing all required inputs. The budget impact assessment will be presented at the initial investment decision and a summary will be included in the business case, IP&A Independent Evaluation Review briefing, and other documents as required.   The evaluation will include a review of the current Capital Investment Plan against the investment cost of the alternatives. IP&A will also review the following documents/activities as part of the budget assessment:

- Resource Planning Document

- Cost Accounting System data review

- All CIP lines and how they align to lifecycle cost estimates

- Operations and Maintenance impacts

- Spend plans

# IP&A Independent Evaluation Review

IP&A is required to perform an independent review of each business case and brief the Chief Financial Officer prior to the initial investment decision. As part of its responsibility, IP&A will perform an economic analysis that will be documented in the business case and presented to the Joint Resources Council.

Example:

IP&A will develop an Independent Evaluation Review which documents the business case of each alternative and includes IP&A findings and recommendations. The review will include the legacy case, costs and benefits, cost risk, schedule risk, economics analysis, and affordability assessment.

# EXIT CRITERIA

The Joint Resources Council Checklist outlines the standard artifacts required to achieve an initial investment decision. In addition, IP&A and other stakeholders develop exit criteria for initial investment analysis which includes any critical analyses and documentation that may not have been fully developed during concept and requirements definition.

Example:

The following artifacts will be completed during initial investment analysis in preparation for the initial investment decision:

- (List all analyses and documents that will be completed during initial investment analysis)

# Decision Briefing

A JRC decision briefing summarizing the business case of each alternative is prepared and briefed to the Joint Resources Council by the program office.

Example:

The program office will present the business case of each alternative to the Joint Resources Council at the initial investment decision using the standard AMS presentation template. IP&A findings and recommendations will be included in the presentation.

# ROLES AND RESPONSIBILITIES

## Program Office

Describe the overall responsibilities of the program office.

Example:

The (name) program office will lead the investment analysis for (name of initiative) and will work with the investment analysis team, IP&A, JRC Secretariat Staff, and other stakeholder organizations to verify strategy, methodology, and findings. The (name) program office will serve as the integrator for all information gathered from stakeholders including relevant systems engineering stakeholders. The program office will ensure the investment initiative is SWIM-compliant. The program office will consolidate and distribute information, as appropriate, to responsible organizations, leads, and team members to complete all required initial investment decision artifacts.

## Relationship with IP&A

The Office of Investment Planning and Analysis will provide resources to guide the preparation of business case analysis products.

Example:

The investment analysis team will maintain frequent and open communication with IP&A throughout the investment analysis process. Up-to-date knowledge of data and the processes used to produce it are integral to IP&A completing the review on schedule. The analysis will be documented by the team and provided to IP&A for review and evaluation. Adequate time will be provided to review outputs, including draft Basis of Estimate and supporting documentation.

The Office of Investment Planning and Analysis will provide resources to guide the preparation of business case analysis products. At the onset of the analysis, IP&A and (program office name) will agree on the approach to estimate, risk adjust, and present schedule, costs and benefits. In addition IP&A will review the initial acquisition approach of each alternative and provide input to any CFO review as required.

Organizational Leads:

| Name | Organization | Role/Responsibility |
| --- | --- | --- |
| Lead business case analyst | Finance, Investment Planning and Analysis Office | Business case analysis and independent review |
| Lead program office person | Service Unit, xxx Program Office | Manages investment analysis team activity and ensures quality |

Include a complete list of investment analysis participants and their responsibilities in Appendix A.

##### APPENDIX A:  INVESTMENT ANALYSIS TEAM COMPOSITION

Example:

Table A-1 identifies members of the investment analysis team and summarizes their role. Team membership includes all organizations and stakeholders impacted by the initiative to ensure the quality of the analysis and success of any resultant investment program. Ownership of (name of initiative) resides with the (name of program office). Team composition may be revised during the analysis to ensure the appropriate skill set is available.

Table A-1: Team Composition

|  | Program IA Team |  |  |
| --- | --- | --- | --- |
| Name | Roles | Organization | Telephone |

APPENDIX B:  INVESTMENT ANALYSIS SCHEDULE

The schedule for IID covers the activities required to complete all JRC Checklist items and the review/signature processes. It also covers the activities required to complete all acquisition activities (e.g., Market Survey, Screening Information Request), and the review/signature process. Resource loading and statistical risk analysis are not required. While the IAP shows a summary of the IA schedule, the IA schedule should be developed in a tool that allows critical path analysis and evaluation of program status.

Sample Initial Investment Analysis Schedule

https://ksn2.faa.gov/afn/jrcportal/Shared%20Documents/JRC%20Readiness%20Criteria%20Checklist.pdf#Home

https://ksn2.faa.gov/afn/jrcportal/Shared%20Documents/JRC%20Readiness%20Criteria%20Checklist.pdf#Home

See Business Case Analysis Guidance; Appendix A: Business Case Requirements.

https://ksn2.faa.gov/afn/jrcportal/Shared%20Documents/JRC%20Readiness%20Criteria%20Checklist.pdf#Home

## GAO Schedule Assessment Guide, dated May 2012, Ten Best Practices. http://www.gao.gov/assets/600/591240.pdf